## PROJECT SCHEDULE
Project Schedule | [8 empty] | https://www.smartsheet.com/try-it?trp=10689&utm_source=template-google-sheet&utm_medium=content&utm_campaign=Project+Schedule-google-sheet-10689&lpa=Project+Schedule+google-sheet+10689
Project Name |  |  |  |  | Start Date
TSOLOM BRIDGE PROJECT |  |  |  |  | 2025-09-12
Project Manager |  |  |  |  | End Date
BRIDGEWORKS COLLECTIVE |  |  |  |  | 2026-04-22
|  | Timeline |  |  | Project Notes
Main Phase | SUB - Phase Title | Start Date | End Date | Duration (in days) | Schedule | Budget | Resources | Issues | Comments | Schedule
Conceptual Design | Startup & Info Gathering | 2025-09-15 | 2025-09-20 | 6 | On Track | 4500 | PM, Research Lead |  | Stakeholder kickoff completed | On Track
| Design Proposal Submission | 2025-09-21 | 2025-09-25 | 5 | On Track | 12000 | UX, UI Designer, Product Owner |  | Proposal submission scheduled 09/25/2025 | Slightly Behind
| Option Development (Truss, Girder, Cable-stayed, etc.) | 2025-09-26 | 2025-10-05 | 10 | On Track | 22000 | Structural Lead, Concept Designer |  |  | Not Started
| MAE + WDM Evaluation | 2025-10-06 | 2025-10-06 | 1 | On Track | 22000 | Structural, Environmental, Cost Analysts
| Conceptual Report & Presentation | 2025-10-07 | 2025-10-25 | 19 | Not Started | 25000 | PM, Documentation Lead
Preliminary Design (Nov–Dec 2025) | Preferred Option Development | 2025-11-01 | 2025-11-15 | 15 | Not Started | 8000 | Structural & Geotech Leads
| Stuctural, Geotech & Hydrotechnical Feasibility | 2025-11-16 | 2025-11-25 | 10 | Not Started | 6500 | Geotech, Hydro Lead
| Iteration & Option Re-evaluation | 2025-11-26 | 2025-11-30 | 5 | Not Started | 3200 | PM, Structural Lead
| Constructability & Access Study (updated with iterations) | 2025-12-01 | 2025-12-05 | 5 | Not Started | 3200 | Constructability Lead, Logistics
| Preliminary Report & Class C Estimate | 2025-12-06 | 2025-12-15 | 10 | Not Started | 3200 | PM, Cost Lead
Detailed Design (Jan–Apr 2026) | Hydrotechnical & Scour Design | 2026-01-10 | 2026-01-25 | 16 | Not Started | 3200 | Hydro Engineer, Geotech
| Geotechnical Design & Foundations | 2026-01-26 | 2026-02-15 | 21 | Not Started | 3200 | Geotech Lead, Structural
| Structural Analysis & Member Design | 2026-02-16 | 2026-03-10 | 23 | Not Started | 3200 | Structural Team
| Detailing & Suicide-Barrier Integration | 2026-03-11 | 2026-03-25 | 15 | Not Started | 3200 | Structural, Safety Lead
| Trail Integration & Environmental Permitting | 2026-03-26 | 2026-04-05 | 11 | Not Started | 3200 | Environmental, Landscape, PM
| Final Report, Drawings & Class A Estimate | 2026-04-06 | 2026-04-20 | 15 | Not Started | 3200 | PM, Documentation Lead
| Enter Text |  |  | 1
Delivery Timeline

## PROJECT TASKS
Phase | Key Tasks / Deliverables
Conceptual Design (Sept–Oct 2025) | • Define project scope & objectives (span, constraints, loads) • Gather background info: site context, environmental & stakeholder needs • Preliminary site reconnaissance / desk study • Regulatory, permits & constraints scan • Identify load cases: pedestrian, equestrian, ATVs • Generate options: bridge types & alignments • Initial cost & risk estimates • Select preferred option • Deliver conceptual design package: sketches, option comparisons, high-level cost & risk
Preliminary Design (Nov–Dec 2025) | • Refine site investigations: topo survey, geotech, hydrology, utilities mapping • Develop detailed design criteria (codes, loads, materials) • Structural analysis of preferred option(s), preliminary sizing • Begin environmental permitting, stakeholder consultations • More detailed cost estimating: lifecycle, construction, maintenance • Risk assessment and mitigation • Input from consultants (geotech, hydraulics, electrical) • Prepare preliminary drawings: alignment, elevation, structural scheme • Assess constructability, maintenance, durability • Deliver preliminary design report: refined option, drawings, Class C estimate, stakeholder feedback
Detailed Design (Jan–Apr 2026) | • Complete site investigations and geotech/hydrology reports • Final structural design: member sizing, foundations, connections • Advanced load cases and detailed modeling (FEM, seismic, vibration) • Produce detailed drawings and specifications (plans, sections, details) • Final Class A cost estimate with contingencies • Construction staging and phasing plan • Environmental monitoring & mitigation finalized • Final stakeholder consultations & reviews • Deliver construction-ready package: full design report, specifications, bid-ready drawings