## WDM
Metrics / Weights |  | Option 1 |  |  | Option 2 |  |  | Option 3 |  |  | Weighting Decisions
Metric | Weighting | Score (0-10) | Weighted Score | Plan / Justification | Score (0-10) | Weighted Score | Plan / Justification | Score (0-10) | Weighted Score | Plan / Justification | Metric | weightings /10 | Scaled Weightings
Cost | 0.17949 | 5.0941 | 0.91433 | familiar analysis/design workflow; minimal cable dynamics; standard erection planning. | 5 | 0.89744 | This is the highest cost and thus the lowest score due to the high complexity of the design and thus the amount of time that would have to go into it | 10 | 1.7949 | Cable dynamics, exrtra piers required for the existing north and south end bridge spans | Cost | 7 | 0.17949 | For scoring of each element of WDM weightings we score from 1-10 where one means its the worst in this sector and 10 means its the best
Constructability | 0.10256 | 5 | 0.51282 | Very difficult access + steep slopes = high-risk erection. Cantilever construction could reduce falsework but adds complexity. Erosion factor on slope will require deep foundation work for anchoring in to the side of the slope posing an different challenge than other bridge desings | 3 | 0.30769 | Complex hybrid suspension - would require more materials and construction complexity | 7 | 0.71795 |  | Constructability | 4 | 0.10256
Environmental Effect | 0.17949 | 5 | 0.89744 | Minimal long-term impact once built: fewer piers needed in waterways, preserving flow and ecosystems. However, construction staging and excavation can be disruptive in sensitive environments. | 3 | 0.53846 | Requires large foundations and multiple around, but overall not too bad | 6 | 1.0769 | Dont fuck the fish | Environmental Effect | 7 | 0.17949
Property Impact | 0.076923 | 7 | 0.53846 | Requires large abutments on slopes, affecting land use and possibly private property. | 6 | 0.46154 | Large footprints at the ends of the bridge - which requires more space | 8 | 0.61538 |  | Property Impact | 3 | 0.076923
Revenue Generation | 0.10256 | 6.5 | 0.66667 | In a study 1 person said this bridge would generate the most traffic due to the bridge being coolest, Iconic arch form could become a landmark bridge. Potential boost for local identity/tourism. | 5 | 0.51282 | In a study 5 person said this bridge would generate the most traffic due to the bridge being coolest | 1 | 0.10256 | In a study 1 person said this bridge would generate the most traffic due to the bridge being coolest | Revenue Generation | 4 | 0.10256
User Comfort | 0.20513 | 8 | 1.641 | Very smooth ride once built; arch offers stiff and visually appealing crossing. | 6 | 1.2308 | Smooth, modern and aestetic | 9 | 1.8462 |  | User Comfort | 8 | 0.20513
Maintenance | 0.15385 | 7 | 1.0769 | Concrete arch: relatively low upkeep, but drainage on slopes is a weak point. Steel arch: higher inspection/painting demand, but avoids slope reinforcement issues. | 5 | 0.76923 | Requires ongoing and detailed cable inspections | 8 | 1.2308 |  | Maintainance | 6 | 0.15385
Total weightings | 1 | 6.2477 |  |  | 4.7179 |  |  | 7.3846 |  |  | Total | 39 | 1
Bridge Type |  | Arch |  |  | Hybrid Suspension |  |  | Extra Dosed Cable Stay bridge
Bridge Mockup

## Costs (NET + Construction + Sca
Construction Cost Breakdowns
| Scaled out of 10 (off of min) | [5 empty] | How I’m estimating (quickly) Urban base cost from comparable bridges (unit $/m² × 375 m²): Arch (reference: Peace Bridge, Calgary) — total ≈ C$24.5 M with inside width ~6.2 m and 126–131 m length; implied ~C$30k/m² (iconic finish). Using a non-iconic finish, I assume ~25–35% lower for planning. Wikipedia Cable-stayed (reference: Sundial Bridge, Redding) — US$23.5–$24 M at ~1,496 m² → ~US$15.7k/m² (≈ C$21.7k/m²). Wikipedia Hybrid suspension (your definition = suspension + side stays) — no perfect twin; use the Kurilpa total (A$63 M, 470 m × 6.5 m) to sanity-check pedestrian cable/stay complexity (unit A$~20.6k/m² on full area), then place hybrid slightly above cable-stayed for similar span. Wikipedia +1 Remote-site adders (applied to direct works): Mobilization: manuals note higher mobilization in remote areas; >10% can be justified for staging/multiple seasons. I’ll use 12%. Federal Highway Administration +1 Heavy transport & lifts (prefab arches/segments, barge/road haul): 8%. (Method follows DOT guidance to treat as separate allowance on direct works.) NJ.gov Temporary works & erection engineering (falsework, cable stressing gear, temporary towers): 6%. NJ.gov Environmental compliance (fish windows, turbidity control, spill response, monitoring/permits): 4%. → Combined remote/staging uplift on direct works = ~30%. Then add Contractor OH&P 15%, and a planning contingency 30% (long-span bridge; remote uncertainty). (These ranges are consistent with DOT planning practice and remote case memos.) NJ.gov +1 Note: FHWA “$150–$250/ft²” pedestrian figures are a low baseline for short/simple spans and understate 125 m signature types—used only as a floor check. ced.sog.unc.edu A) Arch (steel tied-arch / truss-arch) Urban base (planning): Iconic Peace-like unit (C$~30k/m²) × 375 m² ≈ C$11.3 M (very high finish). Non-iconic planning baseline (−25–35%): ≈ C$7.5–8.5 M. I’ll use C$8.0 M as base. Wikipedia Remote adjustments Remote & staging uplift (30% of base): +C$2.40 M → C$10.40 M. Federal Highway Administration +1 Contractor OH&P (15%): +C$1.56 M → C$11.96 M. NJ.gov Contingency (30% planning): +C$3.59 M → ≈ C$15.6 M total. Arch construction planning estimate (remote): ≈ C$15.6 M (range C$14–17 M). B) Cable-stayed (single pylon/towers + stays) Urban base from Sundial unit: ~C$21.7k/m² × 375 m² ≈ C$8.13 M. Wikipedia Remote adjustments Remote & staging uplift (30%): +C$2.44 M → C$10.57 M. Federal Highway Administration Contractor OH&P (15%): +C$1.59 M → C$12.16 M. NJ.gov Contingency (30%): +C$3.65 M → ≈ C$15.8 M total. Cable-stayed construction planning estimate (remote): ≈ C$15.8 M (range C$14.5–17.5 M). C) Hybrid suspension (main suspension + side stays) Urban base (placed slightly above stayed due to dual systems): Assume C$8.5 M baseline (between Sundial unit and Kurilpa-style complexity; same span). Wikipedia +1 Remote adjustments Remote & staging uplift (30%): +C$2.55 M → C$11.05 M. Federal Highway Administration Contractor OH&P (15%): +C$1.66 M → C$12.71 M. NJ.gov Contingency (30%): +C$3.81 M → ≈ C$16.5 M total. Hybrid-suspension construction planning estimate (remote): ≈ C$16.5 M (range C$15–18.5 M).
Option | Cost from chat (left) (Millions in CAD) | Scaled to out of 10 | Option | Estimate of Construction Costs | Total Cost (design + construction) | Scaled to out of 10
Option 1 (Arch) | 1315721.2 | 9.8927 | Option 1 (Arch) | 17000000 | 18315721.2 | 5.0941
Option 2 (Hybrid) | 1839013.06 | 7.0778 | Option 2 (Hybrid) | 16500000 | 18339013.06 | 5
Option 3 (Stayed) | 1301607.94 | 10 | Option 3 (Stayed) | 15800000 | 17101607.94 | 10
Min | 1301607.94 | 10 | Min | 15800000 | 17101607.94 | 0.7611
1214113.26
1237405.12
Formula: | (1/(C5/$C$8))*10 |  |  |  | 0
1237405.12

## Cost Estimate (Arch)
1) Arch / tied-arch (baseline complexity)
Role | Hours | Rate | Cost
Project Manager (E5) | 280 | 299 | 83720
Senior Engineers (E4) | 820 | 274 | 224680
Project Engineers (E3) | 2000 | 219 | 438000
Technologists (T4/T5 avg) | 1100 | 216 | 237600
Admin | 160 | 80 | 12800
Subtotal (fees) | 5760 | — | 996800
Normal disbursements (8%) | — | — | 79744
Disbursment Type | Estimated Cost | Markup to Client | Cost
Project Specific Disbursments | 45000 | 10% | 49500 | BC extras: environmental permits, Indigenous consultation, seismic hazard modelling
Subconsultants (Geotech + Env.) | 70000 | 5% | 73500 | Boreholes, site classification, environmental assessment
Subcontractors (Traffic counts, drilling) | 40000 | 10% | 44000 | Exploratory site works
Subtotal (fees + disbursments) | — | — | 1243544
Tax Type | Applied on what? | Tax Rate | Cost
GST | Fees + disbursments | 5% | 62177.2
PST | Software + Goods | 7% | 10000
Total arch design fee |  |  | 1315721.2
Why fewer hours: familiar analysis/design workflow; minimal cable dynamics; standard erection planning.

## Cost Estimate (Hybrid)
2) Hybrid suspension (main suspension + side stays) — higher than cable-stayed
Role | Hours | Rate | Cost
Project Manager (E5) | 360 | 299 | 107640
Senior Engineers (E4) | 1050 | 274 | 287700
Project Engineers (E3) | 2650 | 219 | 580350
Technologists (T4/T5 avg) | 1450 | 216 | 313200
Admin | 190 | 80 | 15200
Subtotal (fees) | 5760 | — | 1304090
Normal disbursements (8%) | — | — | 104327.2
Disbursment Type | Estimated Cost | Markup to Client | Cost
Project Specific Disbursments | 90000 | 10% | 99000 | BC extras: suspension cable monitoring, fisheries permitting, Indigenous engagement, seismic peer review
Subconsultants (Geotech + Cable dynamics + Env.) | 150000 | 5% | 157500 | Deep soil boreholes, cable dynamics specialist, environmental study
Subcontractors (Drilling, traffic counts, archaeologist) | 70000 | 10% | 77000 | Exploratory services
Subtotal (fees + disbursments) | — | — | 1741917.2
Tax Type | Applied on what? | Tax Rate | Cost
GST | Fees + disbursments | 5% | 87095.86
PST | Software + Goods | 7% | 10000
Total hybrid-suspension design fee |  |  | 1839013.06
Why highest: you carry all the cable-stayed tasks plus the suspension system (main cables + hangers + saddles + anchorages + catenary geometry + additional erection modelling), and you must analyze interactions (load sharing, stiffness compatibility, vibration, redundancy). That means more iterations, more drawings/details, and typically an extra independent check.

## Cost Estimate (Cable Stay)
3) Cable-stayed (towers + stays)
Role | Hours | Rate | Cost
Project Manager (E5) | 250 | 299 | 74750
Senior Engineers (E4) | 720 | 274 | 197280
Project Engineers (E3) | 1800 | 219 | 394200
Technologists (T4/T5 avg) | 980 | 216 | 211680
Admin | 150 | 80 | 12000
Subtotal (fees) | 5760 | — | 889910
Normal disbursements (8%) | — | — | 71192.8
Disbursment Type | Estimated Cost | Markup to Client | Cost
Project Specific Disbursments | 70000 | 10% | 77000 | BC extras: wind tunnel allowance, environmental permitting, Indigenous consultation
Subconsultants (Geotech + Wind/Seismic) | 120000 | 5% | 126000 | Boreholes, peer review, seismic specialists
Subcontractors (Site prep, traffic, drilling) | 60000 | 10% | 66000 | Exploratory services
Subtotal (fees + disbursments) | — | — | 1230102.8
Tax Type | Applied on what? | Tax Rate | Cost
GST | Fees + disbursments | 5% | 61505.14
PST | Software + Goods | 7% | 10000
Total arch design fee |  |  | 1301607.94
Why more than arch: tower design, stay-cable forces, damping, aero serviceability, staged construction.